## Sheet1
Stella Link Estimated Timeline | 2024 | [8 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
| Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec
NOFA Issued (HCDD) | bar: 2024 Apr to 2024 Aug
Developer Selection (HCDD) | bar: 2024 Aug to 2024 Oct
Developer Agreement Finalized (HCDD / Developer) | bar: 2024 Nov to 2025 Feb
Project Design (Developer) | bar: 2024 Dec to 2025 July
Infrastructure Development (Developer - Reimbursed by HCDD) | bar: 2025 Apr to 2026 Jan
Construction of Homes (Developer) | bar: 2025 Oct to 2026 Dec
Sale of Homes (Developer) | bar: 2026 Apr to 2027 Dec